## Slide 1: Designing a Safeguards Information system
Presented by
MAMITIANA Andriamanjato
and
JAOZANDRY Jean Jacques
National REDD+ Bureau
MADAGASCAR
Africa Regional South-South Knowledge Exchange on REDD+ Safeguards and Safeguards Information Systems
Accra. 12 – 13 June 2018
Notes: <number>

## Slide 2: National REDD+ Readiness Process
Readiness phase
Implementation phase- PRE
Oct. 2014
Funding from FCPF
November 2017
National Strategy, FRL/NSFM and SIS , MGP, BS
June 2018
Investment plan and National REDD+ national fund
Oct. 2015
ER-PIN approved by the FCPF
Mars. 2018
ER-PA signed with the FCPF
Dec. 2018
National outcomes
2017-2020
Other payments for results agreements
Convergence of additional national and international funding
2015 – mi2017
Baseline analysis
Definition of Strategic options /policies and measures
Arrangements put in place:
- institutional, legal
-financial
National and international policy dialogues: policy integration and legal framework : sector reforms
2008
RPP Formulation
R-PIN
Dec. 2017
ERP Validation by Carbon Fund

## Slide 3: Process : what we have done
  What process did you use to define the information that your SIS will collect and provide (info needs)?
    The process can be summarised as follows: (1) setting up a conceptual framework for the SIS comprised of principles, criteria and indicators (Cancun safeguards adapted to national context), (ii) Establishing a baseline of information available at the level of the two existing REDD+ projects. (iii) Development of a monitoring protocol, (iv) Development of a data base management system and capacity building of users
  What format will you use for collecting the information (PCI, narrative text, model reports) ?
    Questionnaire validated by all stakeholders, especially National Platform (designed and tested, with measurable objectives)
  Have you already defined the functions of your SIS (collection, aggregation, analysis, reporting, dissemination)?
    Yes, see table in next slide
  Do you have a clear idea of existing information systems and relevant sources for the SIS? If NO, have you commissioned specific studies or analyses
    Study commissioned to a service provider to identify information sources and system operations from data collection to dissemination (see diagram)
  Have you identified which institution/agency should host – and/or be responsible for the SIS?
    Ministry of Environment, Ecology and Forests (MEEF) through Regional Coordination Bureau will host the SIS. An MEEF employee will operate it. He will be assisted by the National REDD+ Office on data collection
  Have you considered creating a dedicated web-based platform to share/disseminate information? If so, what should be the key aspects of this web-based platform?
    http://sis-redd-madagascar.webou.net/scripts/
    https://www.bnc-redd.mg/
  Who will be responsible for each function?
  How is your SIS being funded/budgeted?
    Data collection for each project funded by project developers
    Operation of the system ( (materials and equipment, training, etc.): financing planned under the REDD+ strategy
Notes: <number>

## Slide 4: SIS: Institutions and Responsibilities
Institution | Responsibility
PROJECT DEVELOPERS | To provide data from design stage and monitor implementation (screening sheet, Environmental and Social Management Plan, Project Design Document)
Mayor’s Executive Office | Information quality control, on-site verification
Regional REDD+ Coordination Bureau (BRC-REDD) | Monitoring the implementation of safeguard measures, data collection and reconciliation, information quality assurance and control, transmission of reports to the National REDD+ Coordination Bureau (BNC-REDD)/National Platform for dissemination
Monitoring committee for the implementation of safeguard plans | Monitoring safeguards implementation Preparation and transmission of reports to the BRC-REDD/BNCR
Civil society organisations | To organise site visits to monitor and report on the implementation of measures
Regional and national Platforms (PFR/PFN) | To deliberate about the consistency and quality of data acceptable to all stakeholders
Safeguards Technical Group | To propose measures to improve the SIS and the presentation of reports
National REDD+ Coordination Bureau (BNC-REDD) | Gather, analyse, manage and disseminate information, and improve the SIS
Interministerial committe for the Environment (CIME) | Validation of safeguards and co-benefits monitoring report. National reporting to UNFCCC
Independent Observer | Information quality assurance and control
Notes: <number>

## Slide 5: Strengths & Opportunities : What worked
Please provide details of the opportunities including:
  What donors are involved in REDD+ in your country? How has this impacted the objective/design of your SIS?
    The donors are: UN-REDD and the World Bank ( FCPF funds).
    SIS design based on Decision 12/CP.17 of the UNFCCC, FCPF on the need to provide a summary on the implementation of safeguard measures.
    Pilot projects (CAZ, Makira) served as benchmarks for the development of indicators and questionnaires
  Does your SIS have short and long term reporting objectives (initially, REDD+, later, expanding to forest sector or even broader)? Do you have plans to improve your SIS over time?
    Reporting within the national communication framework: every four years
    Reporting on project: yearly
    At present, the SIS report is limited to the national REDD+ programme and projects
    Improvement is planned and will be carried out based on the progress and needs of the programme.
  If the SIS is expected to gather and provide information for the FCPF purposes, how will the SESA and ESMF be used to inform the SIS?
    SIS builds upon SESA and ESFM indicators as well as the Resettlement Policy Framework
Notes: <number>

## Slide 6: Weaknesses & Challenges: What did not work
Please provide details of the challenges you encountered:
  Were there challenges with the timing of the work?
    SESA and Strategy development done at the same time as the SIS design process:  pending inputs. SIS will probably need adjustment to the availability of the final version of the strategy (institutional mechanism, indicators, etc.)
  What about logistics/cost or ensuring participation?
    Isolation renders the study logistics expensive
    Illiteracy makes participation difficult
  Were there any difficulties in obtaining technical contributions from other government ministries?
    Unavailability of information
Notes: <number>

## Slide 7: Lessons: what we can share with others
Please provide details of the lessons including:
  How is the SIS reporting process linked to safeguard implementation?
    Reference documents (SESA, Environmental and Social Management Plan), safeguards documents prepared by project developers; gathering and validation of information collected and reported. Through the monitoring of established indicators and reported information, the SIS will function as a tool to monitor the effective implementation of safeguard measures.
  What institutional arrangements have you developed to carry out the different functions (institutional mandates, information-sharing agreements)?
    National Platform (consultation and validation body)
    Conception and creation of a ‘group of experts on safeguards’
    Responsibility charter, contract established between project developers, National REDD+ Bureau (BNC REDD) and beneficiaries (FPIC)
  Have you developed an institutional diagram/SIS design document that clearly describes how the SIS will function (flow of information)?
    See next slide for institutional framework
    An SIS design document that clearly describes SIS operations was developed, in it we see information management processes and associated data bases (see pages 32-39 of report)
  What training have you planned to ensure that those responsible will be capable of carrying out their required responsibilities?
    Training and maintenance of software and equipment
    Staggered training for operational managers at regional and local levels for data gathering, verification and entry.
Notes:   Formation en cascade pour les responsables opérationnels au niveau régional et local pour la collecte, la vérification et la saisie des informations
<number>

## Slide 8
MADAGASCAR SIS REDD+ ORGANISATIONAL/INSTITUTIONAL FRAMEWORK
Information providers (National, Regional, Local)
National/ Regional REDD+ Coordination Bureaus
National Platform/PFR
SG Ministry Environment
Steering Committee
GTS
Reporting
Periodic reporting
Answers questions
Update information
Collect and centralise data
Coordinates data collection
Receives data
Relaunch/delay
Process
Reconcile
Analyse and assess
Stock
Internal validation
Control
Request for modification
Dissemination
Formatting
Forward (CCNUCC)
Independent assessment of the SIS
Assess performance
Improve SIS
Validate technical resolutions
support ,advice and strategic direction
Define strategic direction
Definition of strategic direction
Deliberate on data consistency
Approve
Monitor
Requests modifications
Assessment of the SIS
Mandate assessment every four years
Improve SIS
Support/advice and strategic direction
Notes: <number>